## Read me
MegaBrain Academy — BlackBelt on Agentic ABM — Module 6 — Program Budget & RACI Template
What this is | A fill-in template for planning one ABM program: target-account count, the campaign goal and KPIs, a task-level budget with an R/A/C/I owner per task, and a 6-week execution calendar.
How to use it | 1. Fill in the Program Setup sheet (accounts, campaign name/goal, KPIs, content deliverables). 2. List every task on the Budget & RACI sheet with its hours, cost, R/A/C/I owner, and which weeks it runs. 3. Track open action items and blockers on the Action Items sheet.
Anonymization note | The original version of this file was one training provider's real client's internal ABM program plan for a live campaign — real target-account count, a named campaign, real budget figures in the client's currency, and task owners identified by personal initials. None of that is reproduced here. This template is populated with a generic, illustrative worked example — "a Fortune 500 industrial client" — using round, made-up numbers and generic role labels (Marketing Lead, Account Manager, SDR, Sales Lead, Executive Sponsor) in place of any real person. Clear every example value before you fill in your own program.
RACI legend | R = Responsible (does the work) A = Accountable (owns the outcome, signs off) C = Consulted (weighs in before it happens) I = Informed (told after)

## Program Setup
MegaBrain Academy — BlackBelt on Agentic ABM — Module 6 — Program Setup — worked example (anonymized: a Fortune 500 industrial client)
Target account count | 20 | Content deliverables
Campaign name | Plant Efficiency Audit | Lead magnets | 3
Campaign goal | Generate at least 8 opportunities worth $400,000 in pipeline | Draft social posts | 10
Our message | Give your plant engineers back their time — automate the manual reliability checks | Email nurture sequences | 2 sequences x 10 emails
|  | Content hubs (personalized) | 20
KPI — engaged target contacts | 15 engaged chief engineers / plant managers | Webinar | 1, with dedicated landing page
KPI — completed audits | 7 completed plant efficiency audits
KPI — stakeholder relationship | +2.5 average improvement in stakeholder relationship score

## Budget & RACI
MegaBrain Academy — BlackBelt on Agentic ABM — Module 6 — Budget & RACI — 6-week execution calendar (illustrative $ figures)
Task | Comments | Hours | Cost ($) | R | A | C | I | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6
Position & set up social profiles | LinkedIn + X | 12 | 0 | MKT | AM |  |  | x
Draft first batch of social posts (10) |  | 6 | 0 | MKT | AM |  |  | x | x
Prepare 3 lead magnets | Adapt existing research where possible | 24 | 0 | MKT | AM | SL |  | x | x | x
Build landing pages (lead magnet + webinar) |  | 16 | 0 | MKT | AM |  |  |  | x | x
Draft 2 nurture sequences (10 emails each) | One per persona | 40 | 0 | MKT | AM | SDR |  |  | x | x | x
Draft exec-persona emails (2) | Plant manager + chief engineer | 8 | 0 | SDR | AM | SL |  |  | x | x
Draft follow-up email |  | 2 | 0 | SDR | AM |  |  |  |  | x
Direct-mail production & send | Courier + branded item | 16 | 4000 | MKT | AM |  | EXEC |  |  | x
Retargeting creative & campaign setup |  | 8 | 0 | MKT | AM |  |  |  |  | x | x
Retargeting media budget |  | 0 | 5500 | MKT | AM |  |  |  |  | x | x | x
Build 20 personalized content hubs | Headline + banner personalization | 10 | 0 | MKT | AM |  |  |  |  | x | x | x
Webinar prep (materials + speaker) |  | 16 | 0 | MKT | AM | SL |  |  |  |  | x | x
Webinar landing page |  | 4 | 0 | MKT | AM | [5 empty] | x
Audit methodology adaptation | Adapt from delivery team | 8 | 0 | AM | SL | EXEC |  |  |  |  | x | x
Run webinar + send recording to no-shows |  | 8 | 0 | MKT | AM | SDR | [6 empty] | x
Adapt proposal / audit-report template |  | 4 | 0 | AM | SL | EXEC | [6 empty] | x
Total
Role legend: MKT = Marketing Lead AM = Account Manager SDR = SDR/BDR SL = Sales Lead EXEC = Executive Sponsor

## Action Items
MegaBrain Academy — BlackBelt on Agentic ABM — Module 6 — Action Items — open questions & blockers
ID | Opened | Description | Owner | Due | Status | Comments
1 |  | Who is the internal "coach"/champion inside the account? | Account Manager |  | Open | Ask at kickoff: who can preview our target-architecture materials before we send them?
2 |  | Meet the champion 1:1 | Account Manager |  | Open | 1. What would you advise us to do to land in the target architecture? 2. Who's the technical reviewer — can you introduce us? 3. Would the account host a workshop with our specialist?
3 |  | Finalize objections, content, and delivery method | All |  | Open
4 |  | Confirm who runs paid advertising | Marketing Lead |  | Open | What, why, and when are we advertising? Build the contact list for targeting first.
5 |  | Set up LinkedIn company page, follow target stakeholders | Marketing Lead |  | Open
6 |  | Decide on conference participation (speaker vs. attendee) | All |  | Open | Track any team member who already spoke at a relevant industry event this year.
7 |  | Decide whether to invest in a dedicated PR contact | Marketing Lead |  | Open
8 |  | Finalize the events calendar | All |  | Open